## Slide 1: Change and Project Management Toolkit Overview and Approach
Created by ex-McKinsey, Deloitte & BCG Strategy Consultants
Confidential

## Slide 2: Introduction
This Change & Project Management Toolkit will help you create a holistic approach within your organization that tackles both project management and change management simultaneously. Indeed, we believe that one should not come without the other. On one hand, project management focuses on defining and implementing projects that will change your organization's structure, job roles, processes, and systems. On the other hand, change management focuses on helping individuals impacted by these changes to adapt and be successful. Far too often, we have noticed that many companies underestimate the importance of change management. The main problem is that if the employees and managers in your organization do not adopt and embrace the new changes, your projects will rarely achieve their expected return on investment.

## Slide 3: Definition What is the main difference between Project Management and Change Management?
Current state
Transition
Target state
Business & Technical Change
Requires a Project Management approach to change the organization structure, job roles, processes, and systems
People change
Requires a Change Management approach to help individuals impacted by the business and technical changes in their company to adapt and be successful

## Slide 4: Problem Projects are the lifeblood or organizations, but many projects fall short of expectations
Many of us have been there. You start off really excited about a project. And then in the middle of the journey, things start to fall apart. Deadlines are missed, deliverables don’t live up to expectations, and key stakeholders start to be dissatisfied.
By some estimates, Projects fail well over half the time.
But why do so many projects with such great potential end up as failures? Based on our experience working for tier-1 management consulting firms over the past 2 decades, we realized that many projects fall short of expectations because of:
Poor project management
Poor change management
Poor sponsorship
Unclear project objectives
Lack of project visibility
Unrealistic expectations
Communication gaps

## Slide 5: Our Solution Our management consulting firm decided to create a Change & Project Management Toolkit that will help you increase the change and project management capabilities of your organization (or your client if you are a management consultant).
Frameworks
Tools
Templates
Step-by-step tutorials
Video Training
Real-life examples
Best practices
Advise from tier-1 management consultants
What’s inside our Toolkits?

## Slide 6: Content The Toolkit includes 2 parts created by ex-Mckinsey, Deloitte and BCG management consultants
I. Change Management
II. Project Management

## Slide 7: The Change & Project Management Toolkit includes frameworks, tools, templates, tutorials, real-life examples, best practices and video training to help you:
  Improve the change management capabilities of your organization with a simple and comprehensive 3-phase change management approach commonly used by Fortune 100 and global consulting firms: (I) Define the change management strategy, (II) Develop the Change Management Plans, (III) Implement, Track and Manage Progress
  (I) Define your change management strategy: (1) Company strategy, (2) Required change to implement the strategy, (3) Business roadmap, (4) Company readiness for change, (5) Structure and size of the change management team, (6) Roles and responsibilities, (7) Guiding principles, (8) Lean change canvas, (9) Change impact assessment, (10) Change management objectives and levers (ADKAR Model)
  (II) Develop your change management plans: (1) Overarching change management plan, (2) Communication plan, (3) Sponsorship plan, (4) Coaching plan, (5) Training plan, (6) Resistance management plan
  (III) Implement, track and manage progress: (1) Governance, (2) Overarching change management plan status report, (3) Communication plan status report, (4) Sponsorship plan status report, (5) Coaching plan status report, (6) Training plan status report, (7) Resistance management plan status report, (8) Change reinforcement
  Understand the top 12 change management frameworks and tools commonly used in most Fortune 500 companies: (1) Kotter’s 8 step Model of Change, (2) McKinsey 7S framework, (3) Burke-Litwin Change Model, (4) Prosci 3-phase process, (5) The Adkar Change Management Model, (6) Lewin's Change Management Model, (7) Change commitment curve, (8) Change personal transition curve, (9) Heart and mind human drivers, (10) Innovation adoption curve, (11) Maslow’s hierarchy of human needs, (12) Four stages of team development
  Improve the project management capabilities of your organization with a simple and comprehensive 3-phase project management approach commonly used by Fortune 100 and global consulting firms: (I) Build a business case and financial model, (II) Initiate the project, (III) Define and implement your project plan
  (I) Build a business case and financial model to get your project approved by the executive committee: (1) Business opportunity & suggested solution, (2) Project objectives and key performance indicators (KPIs), (3) Project scope, approach and high-level plan, (4) Deliverables, activities & key success factors, (5) Strategic Alignment, (6) Value: project initial investment, project costs, additional revenue generated, cost savings, cash flows and net present value, (7) Ease of implementation
  (II) Initiate your project: (1) Project charter, (2) Project challenges and key success factors, (3) RACI matrix, (4) Stakeholder analysis
  (III) Define and implement your project plan: (1) High-level project plan, (2) Detailed project plan, (3) Project dashboard, (4) Parking lot, (5) Punch list, (6) Post-project evaluation report
  Become a more agile organization with a 7-phase approach commonly used by Fortune 500 and global consulting firms: (1) Product Backlog, (2) Sprint Planning, (3) Sprint Backlog, (4) Sprint Execution, (5) Sprint Review, (6) Potentially Shippable Product Increment, (7) Retrospective
Change Management
Project Management

## Slide 8: I. Change Management The first part of the Toolkit includes a summary of the top 12 change management frameworks and tools commonly used in most Fortune 500 companies, and a condensed and practical Change Management 3-Phase Approach to help you undertake the organizational change of your organization.
Phase I: Define the Change Management Strategy
Phase III: Implement, Track and Manage Progress
Company strategy
Required change to implement the strategy
Business roadmap
Company readiness for change
Structure and size of the change management team
Roles & responsibilities
Guiding principles
Change Lean Canvas
Change impact assessment
Change management objectives and levers (ADKAR Model)
Governance
Overarching change management plan status report
Communication plan status report
Sponsorship plan status report
Coaching plan status report
Training plan status report
Resistance management plan status report
Stakeholder management
Change reinforcement
Overarching change management plan
Communication plan
Sponsorship plan
Coaching plan
Training plan
Resistance management plan
Phase II: Develop the Change Management Plans
Top 12 change management frameworks and tools commonly used in most Fortune 500 companies
Kotter’s 8 step Model of Change
McKinsey 7S framework
Burke-Litwin Change Model
Prosci 3-phase process
The Adkar Change Management Model
Lewin's Change Management Model
Change commitment curve
Change personal transition curve
Heart and mind human drivers
Innovation adoption curve
Maslow’s hierarchy of human needs
Four stages of team development

## Slide 9: II. Project Management The second part of the Toolkit includes a traditional Project Management 3-Phase Approach and an Agile approach to help you define and implement your projects effectively and efficiently
Phase I: Build a Business Case & Financial Model
Phase II: Initiate the Project
Project Description
  Business opportunity & suggested solution
  Project objectives and key performance indicators
  Project scope, approach and high-level plan
  Deliverables, activities & key success factors
Project Assessment
  Strategic alignment
  Value (Revenue, Costs, Net present value, ROI, etc.)
  Ease of implementation
High-level project plan
Detailed project plan
Project dashboard
Parking lot
Punch list
Post-project evaluation report
Phase III: Define and Implement your Project Plan
Project charter
Project challenges and key success factors
RACI matrix
Stakeholder analysis
Traditional Approach
Agile Approach
Product Backlog
Sprint Backlog
Sprint Execution
Potentially Shippable Product Increment
Sprint Planning
Sprint Review
Retrospective

## Slide 10: In the next slides, you’ll see a small preview of Phase I of our change management 3-phase approach
Phase I: Define the Change Management Strategy
Phase III: Implement, Track and Manage Progress
Company strategy
Required change to implement the strategy
Business roadmap
Company readiness for change
Structure and size of the change management team
Roles & responsibilities
Guiding principles
Change Lean Canvas
Change impact assessment
Change management objectives and levers (ADKAR Model)
Governance
Overarching change management plan status report
Communication plan status report
Sponsorship plan status report
Coaching plan status report
Training plan status report
Resistance management plan status report
Stakeholder management
Change reinforcement
Overarching change management plan
Communication plan
Sponsorship plan
Coaching plan
Training plan
Resistance management plan
Phase II: Develop the Change Management Plans
Top 12 change management frameworks and tools commonly used in most Fortune 500 companies
Kotter’s 8 step Model of Change
McKinsey 7S framework
Burke-Litwin Change Model
Prosci 3-phase process
The Adkar Change Management Model
Lewin's Change Management Model
Change commitment curve
Change personal transition curve
Heart and mind human drivers
Innovation adoption curve
Maslow’s hierarchy of human needs
Four stages of team development

## Slide 11: Executive Summary - Change Lean Canvas
Describe the change that is happening
Why did we decide to do this change?
Who will be impacted by this change?
What will we do to prepare impacted stakeholders?
When will they be impacted by this change?
What are the business outcomes we want to reach?
What are the business outcomes we are reaching?
What are the next steps?
Enter the name of the change
Change
Name
Enter Business owner name
Business Owner
Enter Change manager name
Change manager
Insert what the employee, customer or user used to be able to do
Insert what the employee, customer or user will be able to do with this new change
Insert the different stakeholder groups impacted by this change
Describe the rational behind the decision to do this change
Insert date
Insert what we will do to ensure proper adoption of the change (i.e. communication, training, pilot group,…)
Insert the business outcomes we want to reach
When available, insert the business outcomes and their source
Include the next steps if any
Enter Change Canvas version & submit date
Submit
Date

## Slide 12: Change Impact Assessment Scale
Low
Complexity of the change
The Complexity of the change depends on how we rated the impact intensity of the “People increase / reduction” change, “System” change, “Process” change, “Organization structure” change and “Culture” change (see below)
Moderate
Medium
High
Extreme
2.System change
Almost no change
Minor changes/enhancements to functionality in an existing system, that is low risk and noncritical
Major changes/enhancements to functionality in an existing system that is business critical but not customer facing
New technology is being introduced, but the key concepts and functionality are not too dissimilar to the old system. System is customer facing and has the potential to create external exposure if the change is managed poorly
New technology is being introduced which requires bringing a new way of thinking to an existing task. System is customer facing and has the potential to create external exposure if the change is managed poorly
3.Process change
Almost no change to current processes
Some change to current processes, however the change is only minor, and the processes are low risk, non-critical and have no impact to customers.
Significant change to several current processes, however the change is not complex, and processes are low risk, non-critical and have a low impact to customers or colleagues
Significant change to a number of business-critical processes, with some of the change being quite complex. Change will be negatively visible to colleagues, and customers if things go wrong.
Radical change to several core business processes. Colleagues and external parties will need to take on new skills to execute processes. Previously automated processes will become manual or vice versa
4.Organization structure change
There is almost no change to structural environment
There are minor changes to team structure
There are some changes to team structure, which will bring a mixed reaction.
There are significant changes to team structure, which is likely to be disruptive and may be considered a negative change by many
There is significant change to structure. This change will be perceived negatively by most. There is a risk of staff attrition as a result
1.People increase / reduction change
There are low reductions in headcount predicted (~1 FTE), but natural attrition will account for the numbers
There are reductions in headcount predicted, but natural attrition will account for the numbers
There are reductions in headcount predicted but contractors will account for the numbers
There is a significant reduction in headcount predicted. Redeployment & redundancies will need to be factored in
There is a large headcount reduction required as part of this change. Significant effort will need to be invested in redeployment / redundancy
5.Culture change
Almost no culture change required
There are some aspects of the team culture that need to be changed to support this initiative
There is a significant cultural shift required in the impacted areas to support this change
There is a major cultural change across many teams required to support this change
Culture Change required in all impacted groups to support this initiative
Size of the change
1 team impacted
1 Business Unit
1 Division
Half of the Company
Every employee

## Slide 13: In the next slides, you’ll see a small preview of Phase II of our change management 3-phase approach
Phase I: Define the Change Management Strategy
Phase III: Implement, Track and Manage Progress
Company strategy
Required change to implement the strategy
Business roadmap
Company readiness for change
Structure and size of the change management team
Roles & responsibilities
Guiding principles
Change Lean Canvas
Change impact assessment
Change management objectives and levers (ADKAR Model)
Governance
Overarching change management plan status report
Communication plan status report
Sponsorship plan status report
Coaching plan status report
Training plan status report
Resistance management plan status report
Stakeholder management
Change reinforcement
Overarching change management plan
Communication plan
Sponsorship plan
Coaching plan
Training plan
Resistance management plan
Phase II: Develop the Change Management Plans
Top 12 change management frameworks and tools commonly used in most Fortune 500 companies
Kotter’s 8 step Model of Change
McKinsey 7S framework
Burke-Litwin Change Model
Prosci 3-phase process
The Adkar Change Management Model
Lewin's Change Management Model
Change commitment curve
Change personal transition curve
Heart and mind human drivers
Innovation adoption curve
Maslow’s hierarchy of human needs
Four stages of team development

## Slide 14: Overarching Change Management Plan Open the Excel document “Overarching Change Management Plan” for more details

## Slide 15: Communication channel matrix The Channel Matrix below will give us a comprehensive list of the key communication channels to consider, from face-to-face meetings to newsletters.
Department or enterprise meetings
Group meetings
Focus groups
One-on-one meetings
Road show presentations (by project team)
Town Hall meetings
Team meetings
Brown bag lunches
Training courses and workshops
Face-to-face options
Emails
Bulletin boards
Cafeteria postings
Change booklets
Corporate newsletters (feature section)
Demonstrations
Frequently asked questions (memos or newsletter feature)
Internal memos
Intranet pop-ups
Leaflets
Posters
Project newsletters
Videos
Voicemails
Webcasts
Website (Intranet)
Word of mouth
Alternate communication channels
Marketplace changes
Customer input
Ready-access to information
Employee rumors
Channels not under direct control of management
Channels under direct control of management

## Slide 16: In the next slides, you’ll see a small preview of Phase III of our change management 3-phase approach
Phase I: Define the Change Management Strategy
Phase III: Implement, Track and Manage Progress
Company strategy
Required change to implement the strategy
Business roadmap
Company readiness for change
Structure and size of the change management team
Roles & responsibilities
Guiding principles
Change Lean Canvas
Change impact assessment
Change management objectives and levers (ADKAR Model)
Governance
Overarching change management plan status report
Communication plan status report
Sponsorship plan status report
Coaching plan status report
Training plan status report
Resistance management plan status report
Stakeholder management
Change reinforcement
Overarching change management plan
Communication plan
Sponsorship plan
Coaching plan
Training plan
Resistance management plan
Phase II: Develop the Change Management Plans
Top 12 change management frameworks and tools commonly used in most Fortune 500 companies
Kotter’s 8 step Model of Change
McKinsey 7S framework
Burke-Litwin Change Model
Prosci 3-phase process
The Adkar Change Management Model
Lewin's Change Management Model
Change commitment curve
Change personal transition curve
Heart and mind human drivers
Innovation adoption curve
Maslow’s hierarchy of human needs
Four stages of team development

## Slide 17: Overarching Change Management Plan - Status Report One-page summary
 | March | April | May | June | July | August | Sept | October
Understand the Company’s Strategy |  |  |  |  |  |  |  | 
Understand the Change required to implement the Strategy |  |  |  |  |  |  |  | 
Define your Change Management Strategy |  |  |  |  |  |  |  | 
Identify the Impact of the Change |  |  |  |  |  |  |  | 
Develop a Communication Plan |  |  |  |  |  |  |  | 
Develop a Sponsorship Plan |  |  |  |  |  |  |  | 
Develop a Coaching Plan |  |  |  |  |  |  |  | 
Develop a Training Plan |  |  |  |  |  |  |  | 
Develop a Resistance Management Plan |  |  |  |  |  |  |  | 
Implement, Track & Manage Progress |  |  |  |  |  |  |  | 
Reinforce the Change |  |  |  |  |  |  |  | 
On track or completed
Slightly behind
Significantly behind

## Slide 18: Communication Plan - Status Report Open the Excel document “Communication Plan” for more details
This structured communication plan will help us present the right messages, at the right time, in the right format, and from the right sender.

## Slide 19: In the next slides, you’ll see a small preview of some change management frameworks and tools commonly used in most Fortune 500 companies
Phase I: Define the Change Management Strategy
Phase III: Implement, Track and Manage Progress
Company strategy
Required change to implement the strategy
Business roadmap
Company readiness for change
Structure and size of the change management team
Roles & responsibilities
Guiding principles
Change Lean Canvas
Change impact assessment
Change management objectives and levers (ADKAR Model)
Governance
Overarching change management plan status report
Communication plan status report
Sponsorship plan status report
Coaching plan status report
Training plan status report
Resistance management plan status report
Stakeholder management
Change reinforcement
Overarching change management plan
Communication plan
Sponsorship plan
Coaching plan
Training plan
Resistance management plan
Phase II: Develop the Change Management Plans
Top 12 change management frameworks and tools commonly used in most Fortune 500 companies
Kotter’s 8 step Model of Change
McKinsey 7S framework
Burke-Litwin Change Model
Prosci 3-phase process
The Adkar Change Management Model
Lewin's Change Management Model
Change commitment curve
Change personal transition curve
Heart and mind human drivers
Innovation adoption curve
Maslow’s hierarchy of human needs
Four stages of team development

## Slide 20: Terms and Definitions according to Kotter
Change : The transition from a current state to a future state
Change Management : The practice of applying a structured approach to transition an organization from a current state to a future state to achieve expected benefits
Change Impact : How people, process, technology, and the workplace are affected during the transition from the current state to the future state.
Current State: The condition at the time the change is initiated.
Future State: The condition at the time when the benefits have been realized.

## Slide 21: Description of the Kotter’s 8 step Model of Change
Kotter’s 8 Step Change Management Model is a process designed to help leaders successfully implement organizational change.
This model was developed by John P. Kotter, a Harvard Business School professor, and presented in his book “Leading Change,” which was based on years of research that showed that there’s only a 30% chance of effective organizational change implementation.

## Slide 22: The Model walks you through the process of initiating, managing, and sustaining change in eight steps
1
Create Urgency
2
Form a Powerful Coalition
3
Create a Vision for Change
4
Communicate the Vision
5
Remove Obstacles
6
Create Short-Term Wins
7
Build on the Change
8
Anchor the Changes in Corporate Culture
Kotter’s 8 step Model of Change
Initiating Change
Sustaining Change
Managing Change

## Slide 23: Step 1: Create Urgency
For change to happen, it helps if the whole company really wants it. Develop a sense of urgency around the need for change. This may help you spark the initial motivation to get things moving.
This isn't simply a matter of showing people poor sales statistics or talking about increased competition. Open an honest and convincing dialog about what's happening in the marketplace and with your competition. If many people start talking about the change you propose, the urgency can build and feed on itself.
Identify potential threats and develop scenarios showing what could happen in the future.
Examine opportunities that should be, or could be, exploited.
Start honest discussions and give dynamic and convincing reasons to get people talking and thinking.
Request support from customers to strengthen your argument.
Description*
Potential Actions*
*Source: “Leading Change” from John P. Kotter

## Slide 24: McKinsey Seven-S Purpose
The McKinsey 7-S framework maps a constellation of interrelated factors that influence an organization's ability to change. It will help you ensure that:
All parts of your Organization are aligned and work in harmony.
Your organization is well organized to achieve its Vision and Strategic Goals.
The McKinsey 7-S Framework was developed in the early 1980s by Tom Peters and Robert Waterman, two consultants working at the McKinsey & Company consulting firm.

## Slide 25: McKinsey Seven-S Description (1/2)
The Seven-S tool is based on the theory that an organization is not just “Structure”, but is comprised of seven elements distinguished by the “hard S” and “soft S”
The 3 “hard S”, Structure, Strategy, and Systems, are practical and easily identifiable. The 4 “soft S”, Skills, Staff, Style, and Shared Values, are somewhat less easily discerned and are less tangible
The Seven-S diagram depicts how each of the element influences, and is influenced by all of the other elements
Continuously evolving and changing, the “soft S” are determined by the people at work in the organization and hence, are difficult to anticipate or to influence. Although subterranean in nature, they can and do have a great impact on the “hard S”
Structure
System
Strategy
Style
Skill
Staff
Shared
Value
Caption:
The 3 “Hard S”
The 4 “Soft S”

## Slide 26: ADKAR Model Purpose
The ADKAR model was developed by Jeff Hiatt in 2003 and it was introduced as a practical tool by Prosci. The ADKAR Model will help us support individuals moving through change by identifying our change management objectives and levers.

## Slide 27: ADKAR Model Description
ADKAR is an acronym
Awareness
Desire
Knowledge
Reinforcement
Ability
CHANGE

## Slide 28: ADKAR Model Each one of the ADKAR Model 5 elements represents a particular objective that the Change Manager will try to achieve.
of the need to change
Awareness
of how to change (and what the change looks like)
Knowledge
to keep the change in place
Reinforcement
to implement the change on a day-to-day basis
Ability
to participate and support the change
Desire

## Slide 29: In the next slides, you’ll see a small preview of Phase I of our traditional project management 3-phase approach
Phase I: Build a Business Case & Financial Model
Phase II: Initiate the Project
Project Description
  Business opportunity & suggested solution
  Project objectives and key performance indicators
  Project scope, approach and high-level plan
  Deliverables, activities & key success factors
Project Assessment
  Strategic alignment
  Value (Revenue, Costs, Net present value, ROI, etc.)
  Ease of implementation
High-level project plan
Detailed project plan
Project dashboard
Parking lot
Punch list
Post-project evaluation report
Phase III: Define and Implement your Project Plan
Project charter
Project challenges and key success factors
RACI matrix
Stakeholder analysis
Traditional Approach
Agile Approach
Product Backlog
Sprint Backlog
Sprint Execution
Potentially Shippable Product Increment
Sprint Planning
Sprint Review
Retrospective

## Slide 30: Lean Business Case Project name: Project description:
Strategic
Alignment
Value
  Ease of implementation
Yes
No
Low
Medium
High
Difficult
Intermediate
Easy
Change Manager
John Doe
Project Sponsor
John Doe
Project Manager
John Doe
$16.3M
Net Present Value

## Slide 31: Project Business Case Framework
5.Strategic
Alignment
6.Value
  7.Ease of Implementation
Project Description
Project Assessment
1.Business opportunity & suggested solution
3.Project scope, approach and high-level plan
4.Deliverables, activities & key success factors
2.Project objectives and key performance indicators (KPIs)

## Slide 32: In the next slides, you’ll see a small preview of Phase II of our traditional project management 3-phase approach
Phase I: Build a Business Case & Financial Model
Phase II: Initiate the Project
Project Description
  Business opportunity & suggested solution
  Project objectives and key performance indicators
  Project scope, approach and high-level plan
  Deliverables, activities & key success factors
Project Assessment
  Strategic alignment
  Value (Revenue, Costs, Net present value, ROI, etc.)
  Ease of implementation
High-level project plan
Detailed project plan
Project dashboard
Parking lot
Punch list
Post-project evaluation report
Phase III: Define and Implement your Project Plan
Project charter
Project challenges and key success factors
RACI matrix
Stakeholder analysis
Traditional Approach
Agile Approach
Product Backlog
Sprint Backlog
Sprint Execution
Potentially Shippable Product Increment
Sprint Planning
Sprint Review
Retrospective

## Slide 33: Project Charter (Template #1) Project name: Sponsor:
Insert in this box what business issue this project will address
Insert in this box the objective of this project
Problem statement
Objective
Insert what is in-scope
Insert what is in-scope
Insert what is in-scope
Insert what is in-scope
Insert what is in-scope
Insert what is in-scope
In-scope
Insert what is out-of-scope
Insert what is out-of-scope
Insert what is out-of-scope
Insert what is out-of-scope
Insert what is out-of-scope
Insert what is out-of-scope
Out-of-scope
Budget: Insert your own text
Project Manager: Insert your own text
Key Team Members: Insert your own text
Key Stakeholders: Insert your own text
Resources
Insert the name and target date of the milestone
Insert the name and target date of the milestone
Insert the name and target date of the milestone
Key milestones

## Slide 34: See below 2 additional screenshots
Screenshots
Responsibility Assignment (RACI) Matrix
Stakeholder Analysis Matrix

## Slide 35: In the next slides, you’ll see a small preview of Phase III of our traditional project management 3-phase approach
Phase I: Build a Business Case & Financial Model
Phase II: Initiate the Project
Project Description
  Business opportunity & suggested solution
  Project objectives and key performance indicators
  Project scope, approach and high-level plan
  Deliverables, activities & key success factors
Project Assessment
  Strategic alignment
  Value (Revenue, Costs, Net present value, ROI, etc.)
  Ease of implementation
High-level project plan
Detailed project plan
Project dashboard
Parking lot
Punch list
Post-project evaluation report
Phase III: Define and Implement your Project Plan
Project charter
Project challenges and key success factors
RACI matrix
Stakeholder analysis
Traditional Approach
Agile Approach
Product Backlog
Sprint Backlog
Sprint Execution
Potentially Shippable Product Increment
Sprint Planning
Sprint Review
Retrospective

## Slide 36: Project Dashboard (Template #2) Project Name: Insert your own text Project Manager: Insert your own text
Time / Deadlines
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Cost / Budget
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Insert your own text - Insert your own text
Requirement / Quality
  Key Past Milestones
  Key Current Milestones
  Key Future Milestones

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone

Insert Milestone
Overall Status

## Slide 37: Parking Lot Description
IDEA/REQUEST | DELIVERABLE | TIMELINE | CONTACT PERSON | KEY ACTION
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
Insert your own text | Insert your own text | Insert your own text | Insert your own text | Insert your own text
What would be the deliverables required to do it?
When do you need this done?
Who is accountable?
Key action to be taken to complete the request
What would you like to do?

## Slide 38: In the next slides, you’ll see a small preview of the Agile approach
Phase I: Build a Business Case & Financial Model
Phase II: Initiate the Project
Project Description
  Business opportunity & suggested solution
  Project objectives and key performance indicators
  Project scope, approach and high-level plan
  Deliverables, activities & key success factors
Project Assessment
  Strategic alignment
  Value (Revenue, Costs, Net present value, ROI, etc.)
  Ease of implementation
High-level project plan
Detailed project plan
Project dashboard
Parking lot
Punch list
Post-project evaluation report
Phase III: Define and Implement your Project Plan
Project charter
Project challenges and key success factors
RACI matrix
Stakeholder analysis
Traditional Approach
Agile Approach
Product Backlog
Sprint Backlog
Sprint Execution
Potentially Shippable Product Increment
Sprint Planning
Sprint Review
Retrospective

## Slide 39: What is Agile?
Agile is a Mindset
Described by 4 values
Defined by 12 principles
Agile comes to life through an unlimited number of practices
DOING
AGILE
BEING
AGILE

## Slide 40: Scrum methodology
1. PRODUCT BACKLOG
3. SPRINT BACKLOG
4. SPRINT EXECUTION
6. POTENTIALLY SHIPPABLE PRODUCT INCREMENT
SPRINT
1-4 Weeks
STANDUP
15 min, Daily
2. SPRINT PLANNING
1 day
5. SPRINT REVIEW
7. RETROSPECTIVE

## Slide 41: Product backlog template
Product Backlog Item | Priority | User Story | Acceptance Criteria | Estimate | Dependencies
[Name of item] | [1, 2, 3, etc.] | As a [user], I want [goal/desired outcome], so that [reason] | [List of criteria that must be met for the item to be considered complete] | [Size of item in story points] | [Other items that this item depends on]
[Name of item] | [1, 2, 3, etc.] | As a [user], I want [goal/desired outcome], so that [reason] | [List of criteria that must be met for the item to be considered complete] | [Size of item in story points] | [Other items that this item depends on]
[Name of item] | [1, 2, 3, etc.] | As a [user], I want [goal/desired outcome], so that [reason] | [List of criteria that must be met for the item to be considered complete] | [Size of item in story points] | [Other items that this item depends on]
[Name of item] | [1, 2, 3, etc.] | As a [user], I want [goal/desired outcome], so that [reason] | [List of criteria that must be met for the item to be considered complete] | [Size of item in story points] | [Other items that this item depends on]
[Name of item] | [1, 2, 3, etc.] | As a [user], I want [goal/desired outcome], so that [reason] | [List of criteria that must be met for the item to be considered complete] | [Size of item in story points] | [Other items that this item depends on]

## Slide 42: Structure of the Toolkit The Project & Change Management Toolkit includes 400 Powerpoint slides, 21 Excel sheets and 7 minutes of Video training categorized into multiple folders that you can download on your device immediately after your purchase.
II. Develop the Change Management Plans
400 editable Powerpoint slides*
21 editable Excel sheets*
  *Please note that the number of PowerPoint slides and Excel sheets listed is the number of unique slides and sheets. For example, a PowerPoint slide that has been duplicated to facilitate our clients’ understanding only counts for 1 slide.
I. Define the Change Management Strategy
III. Implement, Track & Manage Progress
I. Build a Business Case & Financial Model
IV. Top 12 change management frameworks and tools
II. Initiate the Project
III. Define and Implement your Project Plan
Change Management
Project Management Traditional Approach
36-min Video training
Project Management Agile Approach
7-step Agile Approach

## Slide 43: Key Benefits of our Management Consulting Toolkits
Improve the growth & efficiency of your organization by leveraging Management Consulting Toolkits created by ex-McKinsey, Deloitte & BCG Consultants.
Make a great investment for your career & organization. It cost us US$8M+ over the past 10 years to create all our Toolkits. Get them for a fraction of this cost.
Get a competitive advantage. It’s like hiring Management Consultants to create all the practical Frameworks, Tools & Templates you need.
Get the job done quicker and never start from scratch again with our ready-made and fully editable Frameworks, Tools & Templates in Powerpoint & Excel.
Improve the capabilities of your organization by learning how the Fortune 100 and Global Consulting Firms do it.
Get free support and advice from our ex-McKinsey, Deloitte & BCG Management Consultants.
Decrease your costs. Hiring tier-1 Consultants for a project would cost you $300k+. Way more expensive than our Toolkits, which will last you a lifetime!
Become your organization’s subject matter expert and impress your stakeholders with world-class approaches to resolve common business problems.
Don't reinvent the wheel. We have already worked 30,000+ hours over the past 10 years to create all the Management Consulting Toolkits you need.

## Slide 44: What our clients say about our Toolkits Reviews imported from Facebooks, Amazon and Klaviyo
See more reviews >

## Slide 45: Join the 200,000+ Executives, Consultants & Entrepreneurs already leveraging our Business & Consulting Toolkits to improve the performance of their organization and boost their own career.
Trusted by small and large organizations
Customer satisfaction
Number of countries leveraging our Business & Consulting Toolkits
160+
Number of professionals leveraging our Business & Consulting Toolkits
200,000+
4.8
Daily rate of our ex-McKinsey, Deloitte and BCG Management Consultants
$3k-$4k

## Slide 46: Interested in more than 1 Toolkit? Access all our Toolkits for half the price with our Gold Access
Gold Access
Click here to learn more

## Slide 47: Need additional help on top of our Management Consulting Toolkits? Send us a brief and we’ll find you the right talent from our network of 500 tier-1 Management Consultants (the average daily rate is $3k)
Click here to send us a Project Brief

## Slide 48: Thank you for your attention.
www.domontconsulting.com